## Basel_PD_Risk_Rigister
Risk ID | Risk Type | Description | Impact | Mitigation | Status
R1 | Calibration Risk | Predicted PD may diverge from observed default rates over time | Medium | Periodic recalibration and validation review | Closed
R2 | Data Drift | Portfolio characteristics may change over time | Medium | PSI monitoring and threshold-based investigation | Open
R3 | Model Bias | Potential prediction bias across borrower segments | Low | Independent validation and challenger benchmarking | Closed
R4 | Implementation Risk | Incorrect model implementation may impact score generation | Medium | Validation testing and code review | Closed
R5 | Model Limitation | Logistic Regression may not capture complex nonlinear relationships | Medium | Challenger model assessment (XGBoost, LightGBM, RF) | Open
R6 | Feature Drift | Predictor distributions may change after deployment | Medium | Monthly monitoring and periodic review | Open

## IFRS9_Risk_Rigister
Risk ID | Risk Type | Description | Impact | Mitigation | Status
IFRS9-R1 | Lifetime PD Risk | Simplified lifetime PD estimation may misstate ECL | Medium | Annual validation and recalibration review | Open
IFRS9-R2 | Stage Migration Risk | Incorrect Stage 1/2/3 classification may impact provisioning | High | Monthly stage migration monitoring | Open
IFRS9-R3 | Macroeconomic Overlay Risk | Simplified economic assumptions may understate stress losses | Medium | Scenario testing and governance review | Open
IFRS9-R4 | ECL Calculation Risk | PD/LGD/EAD integration errors may affect ECL estimates | High | Formula validation and reconciliation testing | Closed
IFRS9-R5 | Monitoring Risk | Drift indicators may not identify emerging deterioration promptly | Medium | PSI, PD Drift and ECL Drift monitoring | Open
IFRS9-R6 | Model Impairment Risk | Persistent deterioration may reduce model reliability | High | Materiality assessment and escalation framework | Open